## Plan
Task Name | Subtasks | Segment Name | Assigned to | Task Start Date | Task End Date | Actual End Date | status | comments
Create Github repository |  | Segment-1 | Asit
Technical POC(s) |  | Segment-1 | Rajesh
Project plan creation |  | Segment-1 | Asit
Discover datasets |  | Segment-1 | Dave & Dhanaprakash
Finalize datasets |  | Segment-1 | All | 2021-07-26 | 2021-07-28
Check granularity and quality | Check the quality of data | Segment-1 | Dhanaprakash | 2021-07-27 | 2021-07-28 |  | In-progress
| Record any ETL steps needed | [5 empty] | In-progress
Finalize ETL steps |  | Segment-1 | All | 2021-07-28 | 2021-07-28
Finalize scope |  | Segment-1 | All
Finalize solution architecture |  | Segment-1 | All
Finalize DB design |  | Segment-1 | All
Create logical DB design |  | Segment-1 | All
E-R diagram |  | Segment-1 | Dave | 2021-07-27 | 2021-07-28 |  | In-progress
Create scripts for DB & distribute |  | Segment-1 | Dave | 2021-07-27 | 2021-07-28 |  | In-progress
Blueprint of ML |  | Segment-1 | Asit
Mock up of Dashboard |  | Segment-1 | Rajesh