## Plan
Task Name | Subtasks | Segment Name | Assigned to | Task Start Date | Task End Date | Actual End Date | status | comments
Create Github repository |  | Segment-1 | Asit | 2021-07-26 | 2021-07-26 | 2021-07-26 | complete
Technical POC(s) |  | Segment-1 | Rajesh | 2021-07-26 | 2021-07-26 | 2021-07-26 | complete
Project plan creation |  | Segment-1 | Asit | 2021-07-26 | 2021-07-26 | 2021-07-26 | complete
Discover datasets |  | Segment-1 | Dave & Dhanaprakash | 2021-07-20 | 2021-07-26 | 2021-07-27 | complete
Finalize datasets |  | Segment-1 | All | 2021-07-26 | 2021-07-28 | 2021-07-28 | complete
Check granularity and quality | Check the quality of data | Segment-1 | Dhanaprakash | 2021-07-27 | 2021-07-28 |  | In-progress
| Record any ETL steps needed | Segment-1 | Dhanaprakash |  |  |  | In-progress
Finalize scope |  | Segment-1 | All | 2021-07-26 | 2021-07-29 |  | In-progress
Finalize solution architecture |  | Segment-1 | All | 2021-07-26 | 2021-07-28 | 2021-07-28 | complete
Finalize DB design |  | Segment-1 | All | 2021-07-26 | 2021-07-28 |  | In-progress
Create logical DB design |  | Segment-1 | All | 2021-07-26 | 2021-07-28 |  | In-progress
E-R diagram |  | Segment-1 | Dave | 2021-07-27 | 2021-07-28 |  | In-progress
Create scripts for DB & distribute | Create scripts and upload to repository | Segment-1 | Dave | 2021-07-27 | 2021-07-28 |  | In-progress
| Sample data creation (at least for 20 players in database) | Segment-1 | Dave
Blueprint of ML |  | Segment-1 | Asit | 2021-07-29 | 2021-08-01 |  | Pending
Mock up of Dashboard |  | Segment-1 | Rajesh | 2021-07-29 | 2021-08-01 |  | Pending
Finalize ETL steps |  | Segment-2 | All | 2021-07-28 | 2021-07-28 |  | In-progress